## Slide 1: ESS Vision 2020 Implementation

## Slide 2
Presentation Outline:
To present progress on the elaboration of the ESS Vision 2020 portfolio made since November ESSC;
Describe the prioritisation exercise conducted by VIG;
Present the revised ESS Vision 2020 portfolio;
Outline the next steps with the implementation of the ESS Vision 2020.

## Slide 3
Activity since November ESSC
November ESSC
  Welcomed PG TF work on Vision implementation
  More prioritisation & discussion of strategic risks needed
  Agreed SIMSTAT REDESIGN project
  Agreed to conclude PG TF and activate VIG/VIN
Eurostat Portfolio Management Bureau established
  Eurostat/UK exchange visits on portfolio management
VIG activated
  Eurostat (chair), Belgium, France, Hungary, Italy, Netherlands, Norway, Sweden, Slovenia, UK (deputy chair)
  1st VIG meeting 20 Jan 2015 (rules of procedure, portfolio information pack, portfolio prioritisation, roadmap, ESSC seminar preparation)
VIN members appointed

## Slide 4
REDESIGN
DIGICOM
UA/IPROD
BIGD
DARA
QUAL
SUPP
Prioritisation started from the list of potential VIPs discussed in Nov ESSC
SIMSTAT
ESBRs
VALIDATION
ADMIN
IMS
ESDEN
SERV
DW
In total 15 projects :
Original eight + seven floated in Nov ESSC

## Slide 5
VIG scoring exercise
Used tailored version of Options Analyser Tool – developed by UK academics, underpinned by research into why projects fail
VIG member assessments of projects by their:
  Attractiveness
    Contribution to 5 strategic areas of Vision
    Benefits (costs reduction, quality improvement, burden reduction)
    Architectural fit
    Product enhancement potential
  Achievability
    Degree of challenge
    Capability to deliver
  Affordability
    Project costs in EC
    Project costs in NSIs
    Deployment costs in NSIs

## Slide 6: Strategic Contribution – Original Portfolio (pre PGTF)
Chart: Strategic Driver
| Users | Quality | New Data Sources | Production Process | Dissemination
ESDEN | 22 | 50 | 34 | 76 | 36
ADMIN | 44 | 68 | 82 | 66 | 28
DW | 54 | 36 | 22 | 64 | 74
IMS | 26 | 58 | 38 | 78 | 28
SERV | 28 | 48 | 34 | 82 | 38
SIMSTAT | 28.8889 | 68.8889 | 48.8889 | 80 | 22.2222
Validation | 48 | 80 | 26 | 74 | 50
ESBRs | 62 | 82 | 46 | 82 | 40

## Slide 7
Example plots – attractiveness vs achievability

## Slide 8
Chart: DIGICOM
| 50.666666666666522 | 61.666666666666522 | 48.666666666666508 | 77.333333333333258 | 52.666666666666522 | 66 | 74 | 58.333333333333336 | 67 | 76
Range of Scores | 50 | 60 | 60 | 70 | 70 | 70 | 90 | 70 | 60 | 70
Average | 67

## Slide 9
Chart: IMS
| 40 | 83 | 34.666666666666522 | 11 | 40.333333333333336 | 64.666666666666671 | 59.333333333333336 | 36 | 67.666666666666671 | 77.333333333333258
Range of Scores | 50 | 50 | 60 | 20 | 50 | 60 | 60 | 30 | 60 | 60
Average | 50

## Slide 10
Chart: SIMSTAT +
| 59.333333333333336 | 79.333333333333258 | 37.333333333333336 | 47.666666666666508 | 38.333333333333336 | 59.333333333333336 | 72.666666666666671 | 56 | 85.333333333333258
Range of Scores | 50 | 60 | 30 | 60 | 50 | 30 | 60 | 40 | 40
Average | 46.6667

## Slide 11
But what do the country variations tell us?

## Slide 12
Chart: Average across 12 potential VIPs
| 48.416666666666515
France | 50.8333
Italy | 61.6667
UK | 55
Netherlands | 52.5
Slovenia | 59.1667
Hungary | 54.1667
Belgium | 59.1667
Sweden | 55.8333
Norway | 45
Eurostat | 64.1667
EUROSTAT
UK

## Slide 13
And if we plot all potential VIPs ....

## Slide 14: Portfolio Attractiveness by Achievability
Chart: Attractiveness
| 63.433333333333323
UA / IPROD | 64
BIG | 47
DIGI | 67
ESDEN | 53
Admin | 68
DW | 52
IMS | 50
SERV | 48
SIMSAT | 46.6667
ESBRs | 48
Validation | 67
DARA | 63
DISTRACTION?
COMMIT
DROP?
CAPABILITY?

## Slide 15
A guide – not the answer
Helps us ask the right questions
Combine with views/other evidence

## Slide 16
Revised ESS Vision 2020 Portfolio

## Slide 17: ESS Vision 2020 Portfolio as presented in Nov ESSC
New
On-going
Available business cases
SIMSTAT
REDESIGN
ESBRs
QUAL
VALIDATION
UA/IPROD
DW
SERV
DIGICOM
ESDEN
IMS
ADMIN
DARA
BIGD
SUPP

## Slide 18: Revised ESS Vision 2020 portfolio
New
On-going
Available business cases
SIMSTAT
REDESIGN
ESBRs
QUAL
VALIDATION
DW
SERV
DIGICOM
ESDEN
IMS
ADMIN
DARA
BIGD
SUPP
UA/IPROD
ESS Vision 2020 portfolio of 8 projects

## Slide 19: Revised ESS Vision 2020 portfolio
New
On-going
Mature
SIMSTAT
REDESIGN
ESBRs
VALIDATION
SERV
DIGICOM
ESDEN
ADMIN
BIGD
UA/IPROD
SUPP
IMS
DARA
DW
Support
ESS.VIPs
QUAL

## Slide 20: Strategic Contribution of Original Portfolio to the Five Key Vision Areas
Chart: Strategic Driver
| Users | Quality | New Data Sources | Production Process | Dissemination
ESDEN | 22 | 50 | 34 | 76 | 36
ADMIN | 44 | 68 | 82 | 66 | 28
DW | 54 | 36 | 22 | 64 | 74
IMS | 26 | 58 | 38 | 78 | 28
SERV | 28 | 48 | 34 | 82 | 38
SIMSTAT+ | 28.8889 | 68.8889 | 48.8889 | 80 | 22.2222
Validation | 48 | 80 | 26 | 74 | 50
ESBRs | 62 | 82 | 46 | 82 | 40

## Slide 21: Strategic Contribution of Revised Portfolio to the Five Key Vision Areas
Chart: Strategic Driver
| Users | Quality | New Data Sources | Production Process | Dissemination
ESDEN | 22 | 50 | 34 | 76 | 36
ADMIN | 44 | 68 | 82 | 66 | 28
SERV | 28 | 48 | 34 | 82 | 38
SIMSTAT+ | 28.8889 | 68.8889 | 48.8889 | 80 | 22.2222
Validation | 48 | 80 | 26 | 74 | 50
ESBRs | 62 | 82 | 46 | 82 | 40
BIG | 62 | 62 | 98 | 72 | 48
DIGI | 94 | 54 | 30 | 44 | 96
UA / IPROD | 94 | 60 | 38 | 44.4444 | 80

## Slide 22: Portfolio achievability

## Slide 23: Projects dependencies

## Slide 24: Portfolio affordability
Total estimated development cost | Eurostat | Member States
 | 56.2 M€ (estimate) of which 22.3 M€ given to MS for co-financing (estimate) | 3.5 M€ (estimate)
Please note: no deployment costs included

## Slide 25: Portfolio outcomes one 1 year later
Results from pilot exchange of microdata in internal trade of goods from SIMSTAT and evidence based assessment of variants for REDESIGN of INTRASTAT;
Available interoperability framework for ESBRs;
Inventory and registry of validation rules across ESS;
Available IT infrastructure for secure data exchange among ESS partners by ESDEN;
Catalogue of business services with potential to be shared, pilot tests for ESBRs and validation services, guidelines and proposal for governance of shared services in ESS;
Progress with improved access and methods use and assess quality to administrative data;
Launch of 3 pilots on using Big data;
Launching of digital communication and user analytics project.

## Slide 26: The portfolio minibus
ESS Vision 2020
SIMSTAT
REDESIGN
ESBRs
VALIDATION
SERV
DIGICOM
ESDEN
ADMIN
BIGD
UA/IPROD
FRAMEWORKS
ESSC

## Slide 27: Modernisation of the ESS
ESS Vision 2020
SIMSTAT
REDESIGN
ESBRs
VALIDATION
SERV
DIGICOM
ESDEN
ADMIN
BIGD
UA/IPROD
ESSC
FRAMEWORKS

## Slide 28: Modernisation of the ESS
ESS Vision 2020
Modernisation
Programmes
FRIBS
Social Statistics
Agricultural Statistics
FRIBS
Social Statistics
Agricultural Statistics
ESSC

## Slide 29: Modernisation of the ESS
ESS Vision 2020
FRIBS
Social Statistics
Agricultural Statistics
ESSC
FRAMEWORKS

## Slide 30
Next Steps

## Slide 31
VIG Roadmap
Shows the VIG’s high level thinking/plan
Strategic communication document for the VIG/VIN
Five themes: Portfolio, Projects, Processes, Capability, Communication
Living document

## Slide 32: Next steps: Portfolio and Projects
Portfolio
Further prioritisation with the involvement of VIN;
Prepare ground for May ESSC;
Develop management of strategic risks;
Consider role beyond VIPs;
Projects
Develop business cases for potential new VIPs;
Scrutinise/improve business cases for existing ones;
Develop /incorporate better cost estimates
  - Projects costs compared to available funding
  - Deployment intentions and costs in NSIs

## Slide 33: Next steps: Processes
Portfolio management processes
Develop better management information on project status (eg delivery confidence, risks)
Improve business case process (more clarity on phases, approvals, content)
Portfolio Management Capability
Develop portfolio management capability in Eurostat, and in VIG/VIN
Assess ESS Project/Programme/Portfolio management maturity ?

## Slide 34: Next steps: Communication
Promote Vision and implementation in NSIs, using VIG/VIN;
Develop communication tools, project summaries, portfolio map etc;
Combined VIG/VIN event.

## Slide 35: What is expected from the workshop?
Take note of the progress made in establishing the ESS Vision 2020 portfolio;
Discuss and provide opinion on the revised proposal for the ESS Vision 2020 portfolio;
Give strategic guidance on further necessary adaptations to the projects in the ESS Vision 2020 portfolio;
Indicate possible elements of interest with regard to quality, user analytics and dissemination;
Provide opinion on the next steps.

## Slide 36
Thank you for your attention!