## Work Plan 2012
2012 | Who? | Meetings | Annual results and publications | E11-1 Services | E11-2 Furniture and Health | E12-1 Food, beverages and tobacco | E12-2 Personal Appearance | E13-1 House and Garden | E13-2 Transport, Restaurants and Hotels | Construction 2011 | Construction 2012 | Equipment goods | Other
January | Eurostat / GLs / contractors |  |  |  | Validation - intra-country/cleaning Start of VR 1 9/1 |  |  |  |  | Validation |  | 2011 survey: Start of VR3 3/1
| Countries |  |  |  | Validation -cleaning Spatial adjustment factors via eDAMIS 31/1 | Pre-survey: deadline for new proposals 17/1 Deadline pre-survey: 31/1 |  |  |  | Validation |  | Validation
February | Eurostat / GLs / contractors | Group leader meeting 27/2-29/2 |  |  | Validation Interim QT in VR1 13/2 | Draft group list ready 10/2 |  |  |  | Validation |  | Validation | Questionnaires to NSIs 28/2
| Countries |  |  |  | Validation | Answers to draft group list questions 17/2 | Preview answers to GL |  |  | Validation |  | Validation
March | Eurostat / GLs / contractors | Group leader follow-up meeting 21/3 |  | Evaluation | Validation Finalisation of questions VR 1 2/3 | Overlap Final EU list ready 30/3 | Planning | Preview |  | Validation Start of VR3 1/3 |  | Start of VR4 1/3
| Countries | Group meetings E, N, W: 15-16/3 S: 19-20/3 |  | Evaluation | Validation | Discussion of item list | Discussion of planning proposals | Preview |  | Validation |  | Validation | CPIs via eDAMIS 31/3
April | Eurostat / GLs / contractors |  |  |  | Start VR 2 2/4 Closure of validation 30/4 |  |  |  |  | Calculation of final QT 1/4 | Survey material to NSIs 30/4 | Calculation of final QT 30/4
| Countries |  |  |  | Approval of survey results 30/4 | Price collection/NSI validation |  |  |  | Approval of survey results 1/4 Standard survey report (section 3) via eDAMIS 30/4 |  | Approval of survey results 30/4 Standard survey report (section 4) via eDAMIS 31/5
May | Eurostat / GLs / contractors | Art. 64 WG (3/5) PPP Workshop (Paris) (21-22/5) |  | Annual national results | Annual national results |  | Pre-survey list ready 31/5 | Preview questions to NSIs |  |  |  |  | Use of CPIs for annual national calculations E10-1 and E10-2 surveys
| Countries |  |  |  | Survey report (with section 4) via eDAMIS 31/5 | Price collection/NSI validation |  |  |  |  | Data collection
June | Eurostat / GLs / contractors |  | Press release Nowcast 2011 Press release + SIF on HFCE | Use of results in nowcast | Use of results in nowcast | Validation - cleaning |  |  |  | Use of results in nowcast |  | Use of results in nowcast
| Countries |  |  |  |  | Survey data + report (except section 4) via eDAMIS 15/6 | Pre-survey: deadline for new proposals 29/6 | Preview |  |  | Data collection |  | Salaries via eDAMIS 30/6 Interim report grant 2011-2012 30/6
July | Eurostat / GLs / contractors |  |  |  |  | Validation - intra-country/cleaning Start of VR 1 2/7 | [6 empty] | Salaries validation
| Countries |  |  |  |  | Validation /cleaning Spatial adjustment factors via eDAMIS 31/7 | Deadline pre-survey: 13/7 | Preview answers to GLs |  |  | Data collection Survey data + report (sections 1+2) via eDAMIS 31/7 |  | Salaries validation
August | Eurostat / GLs / contractors | Group leader meeting 29/08-31/08 |  |  |  | Validation | Draft group list ready 14/8 |  |  |  | Validation |  | Salaries validation
| Countries |  |  |  |  | Validation Interim QT in VR1 10/8 | Answers to draft group list questions 22/8 |  |  |  | Validation |  | Salaries validation Rents via eDAMIS 31/8
September | Eurostat / GLs / contractors | Group leader follow-up meeting 19/09 |  |  | Evaluation | Validation | Overlap Final EU list ready 28/9 | Planning | Preview |  | Validation: 1st EU QT to NSIs 1/9 |  | Salaries and rents validation
| Countries | Group meetings E, N, S: 13-14/9 W: 17-18/9 |  |  | Evaluation | Validation | Discussion of item list | Discussion of planning proposals | Preview |  | Validation |  | Salaries and rents validation Table 24, VAT and tips via eDAMIS Health data and report 30/9
October | Eurostat / GLs / contractors |  |  |  |  | Start VR 2 1/10 Closure of validation 31/10 |  |  |  |  | Validation |  | Validation of Table 24, VAT and tips
| Countries |  |  |  |  | Approval of survey results 31/10 | Price collection/NSI validation |  |  |  | Validation |  | Approval of rents and salaries survey results
November | Eurostat / GLs / contractors | PPP WG (20-21/11) | 2011-2010-2009 calculation |  |  | Backcast to 2010 for annual calculation (preliminary TAFs) |  | Pre-survey list ready 30/11 | Preview questions to NSIs | Evaluation | Validation | Evaluation 2011 survey and initialisation 2013 survey 2013 pre-survey list ready 30/11 | Use of results in annual calculation
| Countries |  | 2011-2010-2009 approval |  |  | Survey report (with section 4) via eDAMIS 30/11 | Price collection/NSI validation |  |  | Evaluation | Validation | Evaluation 2011 survey and initialisation 2013 survey
December | Eurostat / GLs / contractors |  | Press release + SIF Results 2011-2010-2009 |  |  |  | Validation /cleaning |  |  |  | Validation: 2nd EU QT to NSIs 15/12
| Countries | [5 empty] | Survey data + report (except section 4) via eDAMIS 15/12 | Pre-survey | Preview |  | Validation | Pre-survey

## Process consumer goods 2011-13
| Consumer goods surveys - process steps | Who | E11-1 Services | E11-2 Furniture and Health | E12-1 Food, Beverages and Tobacco | E12-2 Personal Appearance | E13-1 House and Garden | E13-2 Transport, Restaurants and Hotels
1 | Preview at GLM | GL ESTAT OECD |  |  | 28/02-02/03/11 | 29-31/08/11 | 27/02-29/02/12 | 29/08-31/08/12
2 | Preview at group meetings | NSI GL ESTAT |  |  | W, E, S: 17-18/03/11 N: 21-22/03/11 | N, W, S: 15-16/09/11 E:19-20/09/11 | N,W,E: 15-16/03/12 S:19-20/03/12 | E,N,S: 13-14/09/12 W: 17-18/09/12
3 | Preview questions to NSIs | GL |  |  | May 11 | November 11 | May 12 | November 12
4 | Preview answers to GLs | NSI |  | February 11 | July 11 | February 12 | July 12 | February 13
5 | Planning at GLM | GL ESTAT OECD |  | 28/02-02/03/11 | 29-31/08/11 | 27/02-29/02/12 | 29/08-31/08/12 | 25/02-27/02/13
6 | Planning at group meetings | NSI GL ESTAT |  | W, E, S: 17-18/03/11 N: 21-22/03/11 | N, W, S: 15-16/09/11 E:19-20/09/11 | N, W, E: 15-16/03/12 S: 19-20/03/12 | E,N,S: 13-14/09/12 W: 17-18/09/12 | W,E,S: 14/03-15/03/13 N: 18/03-19/03/13
7 | Pre-survey list ready | GL |  | 31/05/11 | 30/11/11 | 31/05/12 | 30/11/12 | 31/05/13
8 | Pre-survey work | NSI |  | June - July 11 | December 11 - January 12 | June - July 12 | December 12-January 13 | June - July 13
9 | Pre-survey: deadline for new proposals | NSI | 14/01/11 | 30/06/11 | 17/01/12 | 29/06/12 | 14/01/13 | 28/06/13
10 | Deadline pre-survey | NSI | 31/01/11 | 15/07/11 | 31/01/12 | 13/07/12 | 31/01/13 | 15/07/13
11 | Draft group list ready | GL | 11/02/11 | 12/08/11 | 10/02/12 | 14/08/12 | 08/02/13 | 09/08/13
12 | Answers to draft group list questions | NSI | 18/02/11 | 19/08/11 | 17/02/12 | 22/08/12 | 15/02/13 | 16/08/13
13 | Overlap at GLM | GL ESTAT OECD | 28/02-02/03/11 | 29-31/08/11 | 27/02-29/02/12 | 29/08-31/08/12 | 25/02-27/02/13 | 26/08-28/08/13
14 | Discussion of item lists at group meetings | NSI GL ESTAT | W, E, S: 17-18/03/11 N: 21-22/03/11 | N, W, S: 15-16/09/11 E:19-20/09/11 | N, W, E: 15-16/03/12 S: 19-20/03/12 | E,N,S:13/09-14/09/12; W: 17/09-18/09/12 | W,E,S: 14/03-15/03/13; N: 18/03-19/03/13 | N,W,S: 12/09-13/09/13; E: 16/09-17/09/13
15 | Follow-up GLM | GL ESTAT OECD | 23/03/11 | 21/09/11 | 21/03/12 | 19/09/12 | 20/03/13 | 18/09/13
16 | Final EU list ready | GL ESTAT | 31/03/11 | 30/09/11 | 30/03/12 | 28/09/12 | 29/03/13 | 30/09/13
17 | Price collection/NSI validation | NSI | April - June 11 | October - December 11 | April - June 12 | October - December 12 | April - June 13 | October - December 13
18 | Price file + survey report (except section 4) via eDAMIS | NSI | 15/06/11 | 15/12/11 | 15/06/12 | 15/12/12 | 15/06/13 | 15/12/13
19 | Validation - intra-country/cleaning | NSI GL | June 11 | December 11 - January 12 | June 12 | December 12 - January 13 | June 13 | December 13 - January 14
20 | Start of Validation Round 1 | ESTAT | 01/07/11 | 09/01/12 | 02/07/12 | 07/01/13 | 01/07/13
21 | Spatial adjustments factors via eDAMIS | NSI | 31/07/11 | 31/01/12 | 31/07/12 | 31/01/13 | 31/07/13
22 | Validation - analysis of 1st EU QT | NSI GL | July - August 11 | January - February 12 | July - August 12 | January - February 13 | July - August 13
23 | Calculation of interim QT in VR 1 | ESTAT | 15/08/11 | 13/02/12 | 10/08/12 | 11/02/13 | 15/08/13
24 | Validation in GLM | GL ESTAT OECD | 29-31/08/11 | 27/02-29/02/12 | 29/08-31/08/12 | 25/02-27/02/13 | 26/08-28/08/13
25 | Finalisation of questions 1st VR | GL | 02/09/11 | 02/03/12 | 04/09/12 | 01/03/13 | 30/08/13
26 | Validation in group meetings | NSI GL ESTAT | N, W, S: 15-16/09/11 E:19-20/09/11 | N, W, E: 15-16/03/12 S: 19-20/03/12 | E,N,S:13/09-14/09/12; W: 17/09-18/09/12 | W,E,S: 14/03-15/03/13; N: 18/03-19/03/13 | N,W,S: 12/09-13/09/13; E: 16/09-17/09/13
27 | Start of Validation Round 2 | ESTAT | 03/10/11 | 02/04/12 | 01/10/12 | 01/04/13 | 01/10/13
28 | Continued validation | NSI GL ESTAT | October 11 | April 12 | October 12 | April 13 | October 13
29 | Approval of survey results and closure of validation | NSI GL | 31/10/11 | 30/04/12 | 31/10/12 | 30/04/13 | 31/10/13
30 | Calculation of annual national results | ESTAT | May 12 | May 12 | May 13 | May 13
31 | Survey report (section 4) via eDAMIS | NSI | 30/11/11 | 31/05/12 | 30/11/12 | 31/05/13 | 29/11/13
32 | Use of survey results in aggregated PPP calculations | ESTAT | December 11 (with preliminary TAFs) | June 12 (nowcast 11) | December 12 (with preliminary TAFs) | June 13 (nowcast 12) | December 13 (with preliminary TAFs)
33 | Evaluation in GLM | GL ESTAT OECD | 27/02-29/02/12 | 29/08-31/08/12 | 25/02-27/02/13 | 26/08-28/08/13
34 | Evaluation in group meetings | NSI GL ESTAT | N, W, E: 15-16/03/12 S: 19-20/03/12 | E,N,S:13/09-14/09/12; W: 17/09-18/09/12 | W,E,S: 14/03-15/03/13; N: 18/03-19/03/13 | N,W,S: 12/09-13/09/13; E: 16/09-17/09/13
|  |  | 2010 | 2011 | 2012 | 2013 | 2014

## Process equipment goods 2011
| Equipment goods surveys - process steps | Who | 2011 survey
1 | Initialisation at Capital Goods WP | ESTAT NSI CE | 11-12/10/10
2 | Pre-survey list ready | CE | 30/11/10
3 | Pre-survey work | NSI | December 10 - February 11
4 | Pre-survey: deadline for new proposals | NSI | 31/01/11
5 | Deadline pre-survey | NSI | 15/02/11
6 | Final EU list ready | CE | 31/03/11
7 | Price collection/NSI validation | NSI | April - June 11
8 | Price file + survey report (sect. 1-4) via eDAMIS | NSI | 30/06/11
9 | Validation - intra-country/cleaning | NSI CE | July 11
10 | Start of Validation Round 1 | ESTAT | 01/08/11
11 | Finalisation of questions 1st VR | CE | 01/09/11
12 | Start of Validation Round 2 | ESTAT | 01/10/11
13 | Use of preliminary results in aggregated PPP calculations | ESTAT | December 11
14 | Finalisation of questions 2nd VR | CE | 01/12/11
15 | Start of Validation Round 3 | ESTAT | 01/01/12
16 | Finalisation of questions 3rd QT | CE | 31/01/12
17 | Start of Validation Round 4 | ESTAT | 01/03/12
18 | Resolving last data issues | ESTAT NSI CE | March - April 12
19 | Approval of survey results and closure of validation | ESTAT | 30/04/12
20 | Survey report (section 5) via eDAMIS | NSI | 31/05/12
21 | Use of survey results in aggregated PPP calculations | ESTAT | June 12
22 | Evaluation in PPP Working Group | ESTAT NSI CE | 19-20/11/12

## Calendar 2012
Main meetings calender 2012
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
January
February | [26 empty] | GLM | GLM | GLM
March | [14 empty] | GE GN GW |  |  |  | GS |  | GLM
April
May | [20 empty] | WS | WS
June
July
August | [28 empty] | GLM | GLM | GLM
September | [12 empty] | GE GN GS |  |  |  | GW |  | GLM
October
November | [19 empty] | WG | WG
December
|  |  |  | Commission closed | [5 empty] | GLM | Group leader meeting
|  |  | WG | PPP WG | [5 empty] | GN | Northern group meeting
|  |  | WS | PPP Workshop (Paris) | [5 empty] | GW | Western group meeting
[10 empty] | GE | Eastern group meeting
[10 empty] | GS | Southern group meeting